## 1-Process Overview
VENDOR RFQ EVALUATION PROCESS FLOW
Document Version: | 1.0
Created Date: | 2025-11-30
Use Case: | HL7/FHIR Integration Platform Selection
Expected Duration: | 3-5 Months
PHASE | STAGE | ACTIVITY | KEY ACTIONS | DECISION GATE | DURATION | DELIVERABLE
Phase 1: Initial Screening | A | Receive RFQ Responses | Collect all vendor proposals by deadline |  | 1 week | Response Repository
| B | Initial Compliance Check | Verify mandatory documents, format, completeness | C: Meets Minimum Requirements? |  | Compliance Matrix
| D | Reject with Feedback | Provide rejection rationale to non-compliant vendors |  |  | Rejection Letters
Phase 2: Detailed Evaluation | E | Detailed Technical Evaluation | Conduct parallel deep-dive analysis across 4 tracks |  | 2-3 weeks
| F | Functional Requirements Scoring | HL7 v2, FHIR R4, transformations, connectors, pre-built integrations |  |  | Functional Scorecard
| G | Technical Capability Assessment | Architecture, scalability, API management, DevOps, monitoring |  |  | Technical Scorecard
| H | Security & Compliance Review | HIPAA, OAuth, encryption, audit logs, certifications (SOC 2, HITRUST) |  |  | Security Scorecard
| I | Commercial Terms Analysis | TCO (3-5 years), licensing model, hidden costs, contract flexibility |  |  | Cost Analysis
Phase 3: Synthesis | J | Create Evaluation Matrix | Weighted scoring: Functional (35%), Technical (30%), Security (20%), Viability (10%), Commercial (5%) |  | 1 week | Weighted Scoring Matrix
| K | Shortlist Top 3-5 Vendors | Rank by total weighted score, select finalists | Select 3-5 vendors? |  | Shortlist Report
Phase 4: Deep Validation | L | Request Clarifications/Demos | Send specific questions, schedule demonstrations |  | 1 week | Clarification Questions
| M | Live Technical Demo | Hands-on demo with actual data, technical Q&A (2-3 hours each) |  | 1-2 weeks | Demo Evaluation Notes
| N | Reference Checks | Contact 3+ customers per vendor, verify claims |  | 1 week | Reference Check Report
| O | Site Visits (Optional) | Visit customer sites to observe production usage |  | 1-2 weeks | Site Visit Report
Phase 5: Final Decision | P | Final Scoring & Ranking | Update matrix with demo/reference insights | Q: Clear Winner? | 1 week | Updated Scoring Matrix
| R | Prepare Recommendation Report | Executive summary, scoring, risks, timeline, budget | If YES |  | Executive Recommendation
| S | BAFO (Best and Final Offer) | Request improved pricing/terms from top 2-3 vendors | If NO |  | BAFO Requests
|  | Loop back to P | Re-score with BAFO information
Phase 6: Approval & Contract | T | Stakeholder Review | Present to IT, clinical, security, compliance, finance teams |  | 2-3 weeks | Stakeholder Sign-off
| U | Executive Approval | Present business case to CIO/CFO/CEO |  |  | Executive Approval
| V | Contract Negotiation | Finalize SLAs, payment terms, IP, liability, exit provisions |  | 4-8 weeks | Signed Contract
| W | Vendor Selection Complete | Transition to implementation phase |  |  | Project Kickoff

## 2-Compliance Checklist
PHASE 1: INITIAL COMPLIANCE CHECK
Instructions: Mark 'Yes', 'No', or 'N/A' for each vendor. Vendors must have 100% 'Yes' on mandatory items to proceed.
Compliance Item | Mandatory? | Weight | Vendor 1 | Vendor 2 | Vendor 3 | Notes | Verification Method
SUBMISSION REQUIREMENTS
Submitted by deadline | Yes | 10% |  |  |  |  | RFQ receipt timestamp
Response in required format (PDF/Word) | Yes | 5% |  |  |  |  | File format check
All sections completed | Yes | 10% |  |  |  |  | Document review
Executive summary included | No | 3% |  |  |  |  | Document review
Authorized signatory signature | Yes | 5% |  |  |  |  | Signature verification
DOCUMENTATION
Company profile and overview | Yes | 5% |  |  |  |  | Document check
Pricing sheet completed | Yes | 10% |  |  |  |  | Pricing review
Technical architecture diagram | Yes | 8% |  |  |  |  | Document check
Implementation methodology | No | 5% |  |  |  |  | Document check
Support and SLA documentation | Yes | 7% |  |  |  |  | Document check
CERTIFICATIONS & COMPLIANCE
HIPAA compliance certification | Yes | 15% |  |  |  |  | Certificate verification
SOC 2 Type II certification | No | 8% |  |  |  |  | Certificate verification
HITRUST certification | No | 5% |  |  |  |  | Certificate verification
ISO 27001 certification | No | 3% |  |  |  |  | Certificate verification
LEGAL & COMMERCIAL
NDA signed and returned | Yes | 10% |  |  |  |  | Legal verification
Insurance certificates (E&O, Cyber) | Yes | 8% |  |  |  |  | Insurance verification
Financial statements (last 2 years) | No | 5% |  |  |  |  | Financial review
Customer references provided (min 3) | Yes | 8% |  |  |  |  | Reference list check
TECHNICAL REQUIREMENTS
HL7 v2 support confirmed | Yes | 10% |  |  |  |  | Technical spec review
FHIR R4 support confirmed | Yes | 10% |  |  |  |  | Technical spec review
Cloud deployment option available | No | 5% |  |  |  |  | Technical spec review
API documentation provided | Yes | 5% |  |  |  |  | Document check
PASS/FAIL DECISION |  |  | Enter: PASS or FAIL | Enter: PASS or FAIL | Enter: PASS or FAIL

## 3-Evaluation Matrix
PHASE 2: DETAILED EVALUATION MATRIX - WEIGHTED SCORING
Vendor Names: | Mirth Connect (Build) |  | InterSystems HealthShare |  | Rhapsody Integration
Requirement Category | Weight | Max Score | V1 Score | V1 Weighted | V2 Score | V2 Weighted | V3 Score | V3 Weighted | Notes
FUNCTIONAL REQUIREMENTS (35%)
HL7 v2 Message Support | 6% | 10 | 9 | 5.4 | 8 | 4.8 | 9 | 5.4 | Mirth:Excellent; ISC:Strong; Rhapsody:Excellent
FHIR R4 Implementation | 6% | 10 | 7 | 4.2 | 9 | 5.4 | 8 | 4.8 | ISC leads in FHIR maturity
Message Transformation & Mapping | 5% | 10 | 8 | 4 | 9 | 4.5 | 8 | 4 | ISC has visual mapper advantage
Data Validation & Quality | 5% | 10 | 7 | 3.5 | 8 | 4 | 8 | 4 | All adequate, Mirth needs custom code
Error Handling & Recovery | 5% | 10 | 7 | 3.5 | 9 | 4.5 | 8 | 4 | ISC has enterprise-grade handling
Routing & Orchestration | 5% | 10 | 8 | 4 | 9 | 4.5 | 7 | 3.5 | ISC BPL engine is superior
Pre-built Connectors | 3% | 10 | 6 | 1.8 | 9 | 2.7 | 8 | 2.4 | Mirth requires custom development
Subtotal - Functional |  |  |  | 26.4 |  | 30.4 |  | 28.1
TECHNICAL CAPABILITIES (30%)
System Architecture | 5% | 5 | 4 | 4 | 5 | 5 | 4 | 4 | ISC is mature enterprise architecture
Performance & Throughput | 5% | 5 | 4 | 4 | 5 | 5 | 4 | 4 | All handle 100K+ msgs/day
API Management | 4% | 5 | 3 | 2.4 | 5 | 4 | 4 | 3.2 | ISC has comprehensive API gateway
Integration Patterns | 4% | 5 | 4 | 3.2 | 5 | 4 | 4 | 3.2 | ISC supports all enterprise patterns
Monitoring & Observability | 4% | 5 | 3 | 2.4 | 5 | 4 | 4 | 3.2 | Mirth needs add-ons for monitoring
DevOps & CI/CD Support | 3% | 5 | 4 | 2.4 | 4 | 2.4 | 3 | 1.8 | Mirth has best Docker support
Data Storage Options | 3% | 5 | 4 | 2.4 | 5 | 3 | 3 | 1.8 | ISC has native data persistence
Standards Compliance | 2% | 5 | 4 | 1.6 | 5 | 2 | 4 | 1.6 | All are standards compliant
Subtotal - Technical |  |  |  | 22.4 |  | 29.4 |  | 22.8
SECURITY & COMPLIANCE (20%)
Authentication & Authorization | 3% | 5 | 3 | 1.8 | 5 | 3 | 4 | 2.4 | ISC has enterprise RBAC
Encryption & Data Protection | 3% | 5 | 4 | 2.4 | 5 | 3 | 4 | 2.4 | All support TLS 1.3
Audit & Compliance Logging | 3% | 5 | 3 | 1.8 | 5 | 3 | 4 | 2.4 | ISC has comprehensive auditing
Regulatory Certifications | 3% | 5 | 2 | 1.2 | 5 | 3 | 4 | 2.4 | Mirth lacks certifications (open source)
Vulnerability Management | 2% | 5 | 3 | 1.2 | 5 | 2 | 4 | 1.6 | Commercial vendors have better processes
Consent Management | 2% | 5 | 2 | 0.8 | 5 | 2 | 3 | 1.2 | ISC has built-in consent framework
Data Privacy Controls | 2% | 5 | 3 | 1.2 | 5 | 2 | 4 | 1.6 | ISC has GDPR-ready features
Network Security | 2% | 5 | 4 | 1.6 | 5 | 2 | 4 | 1.6 | All support VPN, firewall rules
Subtotal - Security |  |  |  | 12 |  | 20 |  | 15.6
VENDOR VIABILITY (10%)
Financial Stability | 2% | 3 | 2 | 1.334 | 3 | 2.001 | 3 | 2.001 | Open source vs established companies
Market Presence & Track Record | 2% | 3 | 2 | 1.334 | 3 | 2.001 | 3 | 2.001 | ISC: 40+ years; Rhapsody: 25+ years
Healthcare Experience | 2% | 3 | 2 | 1.334 | 3 | 2.001 | 3 | 2.001 | All have strong healthcare presence
Support & SLA Guarantees | 2% | 3 | 1 | 0.667 | 3 | 2.001 | 3 | 2.001 | Mirth: community; Others: 24/7 support
Training & Documentation | 1% | 3 | 2 | 0.666 | 3 | 0.999 | 3 | 0.999 | Commercial vendors have better training
Implementation Services | 1% | 3 | 1 | 0.333 | 3 | 0.999 | 3 | 0.999 | Mirth: DIY; Others: full services
Subtotal - Viability |  |  |  | 5.668 |  | 10.002 |  | 10.002
COMMERCIAL TERMS (5%)
Pricing Model Transparency | 1.5% | 4 | 4 | 1.5 | 3 | 1.125 | 3 | 1.125 | Mirth: Free OSS; Others: complex licensing
Total Cost of Ownership (5yr) | 1.5% | 4 | 4 | 1.5 | 2 | 0.75 | 3 | 1.125 | Mirth: $500K; ISC: $2.5M; Rhapsody: $1.8M
Contract Flexibility | 1% | 4 | 4 | 1 | 2 | 0.5 | 3 | 0.75 | Mirth: No lock-in; ISC: rigid terms
Value for Money | 1% | 4 | 3 | 0.75 | 3 | 0.75 | 3 | 0.75 | Depends on internal capabilities
Subtotal - Commercial |  |  |  | 4.75 |  | 3.125 |  | 3.75
TOTAL WEIGHTED SCORE (out of 100) |  |  |  | 71.218 |  | 92.927 |  | 80.252
RATING |  |  |  | Acceptable |  | Excellent |  | Good
RECOMMENDATION | [5 empty] | 🏆 TOP CHOICE

## 4-Demo Evaluation
PHASE 4: LIVE TECHNICAL DEMO EVALUATION
Demo Date: |  |  | Attendees:
Duration: | 2-3 hours |  | Presenter:
Demo Scenario | Evaluation Criteria | Weight | V1 Score (1-5) | V2 Score (1-5) | V3 Score (1-5) | V1 Notes | V2 Notes | V3 Notes
1. HL7 Message Processing
| Receive ADT^A01 message | 10%
| Parse and validate message | 10%
| Handle custom Z-segments | 8%
| Send ACK/NAK response | 7%
2. FHIR Resource Operations
| Create Patient resource | 8%
| Search with complex queries | 8%
| Bulk export demonstration | 7%
| SMART on FHIR authorization | 7%
3. Transformation & Mapping
| HL7 ADT → FHIR Patient | 10%
| HL7 ORU → FHIR Observation | 8%
| Custom field mapping | 7%
4. Error Handling
| Handle malformed message | 7%
| Demonstrate retry logic | 6%
| Show error logging/alerting | 6%
5. Performance & Monitoring
| Show real-time dashboard | 6%
| Demonstrate load handling | 5%
| Tracing & debugging tools | 5%
RED FLAGS OBSERVED
| Cannot demo live system | Critical
| Requires significant custom code | High
| Poor user interface/usability | Medium
| Slow response times | High
OVERALL DEMO ASSESSMENT |  | 100%
PASS/FAIL RECOMMENDATION

## 5-Reference Checks
PHASE 4: CUSTOMER REFERENCE CHECKS
Instructions: Contact at least 3 customers per vendor. Mix of vendor-provided and independently sourced.
VENDOR:
Reference #1 Information
Company Name: |  | Contact Name: | Title:
Industry: |  | Organization Size: | Date of Call:
Implementation Date: |  | Contract Value: | Use Case:
KEY QUESTIONS | Rating (1-5) | Response Summary
Implementation Experience
How smooth was the implementation process?
Were there any surprises or delays?
Did they stay within budget?
Quality of implementation team?
Product Performance
Does the system meet your expectations?
Any performance issues (speed, reliability)?
How does it handle your peak volumes?
System uptime vs. SLA promises?
Support & Maintenance
Quality of technical support?
How quickly do they respond to P1 issues?
Are upgrades/patches smooth?
Have you had any major outages?
Cost & ROI
Any hidden costs or surprise fees?
Maintenance cost increases year-over-year?
Have you achieved expected ROI?
Relationship & Future
How responsive is the account team?
Do they listen to feature requests?
Product roadmap aligned with your needs?
Would you choose them again?
Would you recommend them to others?
RED FLAGS / CONCERNS
OVERALL REFERENCE RATING
Positive Recommendation? (Yes/No)

## 6-BAFO Template
PHASE 5: BEST AND FINAL OFFER (BAFO) REQUEST
Use Case: When top 2-3 vendors are too close to differentiate, request improved terms.
BAFO Request Letter Template
Date: | [Insert Date]
To: | [Vendor Name]
Subject: | Request for Best and Final Offer
Letter Body:
Dear [Vendor Contact],
Thank you for your comprehensive proposal in response to our RFQ for [Project Name].
After careful evaluation, we have shortlisted your solution along with [X] other vendors.
To assist us in our final decision, we invite you to submit a Best and Final Offer (BAFO) by [Date].
Please consider improving your proposal in the following areas:
PRICING & COMMERCIAL TERMS
□ Reduce license fees or subscription costs
□ Offer volume discounts or multi-year pricing
□ Include additional features at no extra cost
□ Reduce or waive implementation fees
□ Improve payment terms (e.g., milestone-based)
□ Cap annual maintenance increases
ADDITIONAL VALUE-ADDS
□ Include additional training hours
□ Extend post-implementation support period
□ Provide dedicated customer success manager
□ Include additional pre-built connectors
□ Offer priority access to new features
IMPROVED SLAs & SUPPORT
□ Enhanced uptime guarantees (e.g., 99.9% → 99.99%)
□ Faster response times for P1/P2 issues
□ Include 24/7 support at base price
IMPLEMENTATION & TIMELINE
□ Accelerated implementation timeline
□ Additional professional services resources
□ Fixed-price implementation guarantee
CONTRACT TERMS
□ More flexible termination clauses
□ Shorter initial term commitment
□ Better IP rights or data portability terms
Submission Instructions:
Please submit your BAFO by [Date] to [Email].
Your revised proposal should include:
1. Updated pricing and commercial terms
2. Summary of improvements vs. original proposal
3. Updated contract terms (if applicable)
4. Confirmation of implementation timeline
This is your final opportunity to improve your offer. We plan to make our selection by [Date].
Sincerely,
[Your Name]
[Title]

## 7-Final Recommendation
PHASE 5: EXECUTIVE RECOMMENDATION REPORT
1. EXECUTIVE SUMMARY
Recommended Vendor: | [Vendor Name]
Total Weighted Score: | [Score out of 100]
Estimated Total Cost (5-year): | $[Amount]
Implementation Timeline: | [X] months
Expected Go-Live Date: | [Date]
Key Strengths:
1. | [Strength 1]
2. | [Strength 2]
3. | [Strength 3]
Key Risks/Gaps:
1. | [Risk 1] | Mitigation: | [Mitigation plan]
2. | [Risk 2] | Mitigation: | [Mitigation plan]
3. | [Risk 3] | Mitigation: | [Mitigation plan]
2. EVALUATION SUMMARY
Total Vendors Evaluated: | [Number]
Vendors in Final Shortlist: | [Number]
Demos Conducted: | [Number]
Reference Checks Completed: | [Number]
Site Visits Conducted: | [Number]
3. SCORING COMPARISON
Category | Winner | Runner-Up #1 | Runner-Up #2
Functional (35%) | [Score] | [Score] | [Score]
Technical (30%) | [Score] | [Score] | [Score]
Security (20%) | [Score] | [Score] | [Score]
Viability (10%) | [Score] | [Score] | [Score]
Commercial (5%) | [Score] | [Score] | [Score]
TOTAL | [Score] | [Score] | [Score]
4. WHY NOT RUNNER-UP VENDORS?
Vendor B: | [Reason not selected]
Vendor C: | [Reason not selected]
5. FINANCIAL ANALYSIS
Component | Year 1 | Years 2-5 | Total (5yr)
License/Subscription | $[Amount] | $[Amount] | $[Amount]
Implementation Services | $[Amount] | $0 | $[Amount]
Training | $[Amount] | $[Amount] | $[Amount]
Annual Maintenance | $0 | $[Amount] | $[Amount]
Infrastructure (cloud/hardware) | $[Amount] | $[Amount] | $[Amount]
Internal FTE costs | $[Amount] | $[Amount] | $[Amount]
TOTAL COST OF OWNERSHIP | $[Amount] | $[Amount] | $[Amount]
6. IMPLEMENTATION PLAN
Phase | Duration | Key Activities | Deliverables
Planning & Kickoff | 4 weeks | Form team, finalize requirements | Project charter, plan
Infrastructure Setup | 6 weeks | Provision environments, network config | Dev/Test/Prod environments
Configuration | 8 weeks | Interface builds, transformations | Configured system
Integration & Testing | 8 weeks | Unit, integration, UAT testing | Test results, sign-off
Training & Documentation | 4 weeks | Train staff, create runbooks | Trained team, docs
Go-Live & Hypercare | 4 weeks | Production cutover, support | Production system
Total Timeline: | 34 weeks (~8 months)
7. RISK ASSESSMENT
Risk | Probability | Impact | Mitigation
Implementation delays | Medium | High | [Mitigation plan]
Integration complexity | Medium | High | [Mitigation plan]
Staff training challenges | Low | Medium | [Mitigation plan]
Vendor support quality | Low | High | [Mitigation plan]
Budget overruns | Medium | High | [Mitigation plan]
8. SUCCESS CRITERIA
Metric | Baseline | Target (12 months) | Measurement
Message processing volume | [Current] | [Target] | System metrics
Integration uptime | [Current] | 99.9% | Monitoring dashboard
Message error rate | [Current] | <0.1% | Error logs
Time to add new interface | [Current] | [Target] | Project tracking
Support tickets (P1/P2) | [Current] | [Target] | Ticketing system
9. NEXT STEPS
Step | Owner | Due Date | Status
Executive approval of recommendation | [Name] | [Date] | Pending
Contract negotiation | [Name] | [Date] | Not Started
Final contract execution | [Name] | [Date] | Not Started
Project kickoff | [Name] | [Date] | Not Started
10. APPROVAL SIGNATURES
Role | Name | Signature | Date
Recommended by: | [Your Name]
Reviewed by (IT): | [CIO/IT Director]
Reviewed by (Clinical): | [CMIO/CNO]
Reviewed by (Security): | [CISO]
Reviewed by (Finance): | [CFO]
Approved by: | [CEO/Executive]

## 8-Lessons Learned
POST-SELECTION: LESSONS LEARNED & BEST PRACTICES
COMMON PITFALLS TO AVOID
Pitfall | Impact | How to Avoid
Skipping compliance check | High | Always verify basic requirements before detailed evaluation
Accepting slide demos instead of live systems | Critical | Require hands-on demos with your actual data/scenarios
Only checking vendor-provided references | High | Find independent references through networking
Ignoring total cost of ownership | High | Calculate 3-5 year TCO including all hidden costs
Rushing to decision | Medium | Follow structured process, don't skip phases
Not involving end users | High | Include technical staff in demos and evaluation
Weak contract negotiation | Critical | Negotiate SLAs, exit clauses, and IP rights upfront
Underestimating implementation time | High | Add 20-30% buffer to vendor timeline estimates
WHAT WENT WELL
Success Factor | Description | Recommendation
[Example: Structured process] | [What worked] | [How to replicate]
WHAT COULD BE IMPROVED
Challenge | Impact | Future Improvement
[Example: Timeline pressure] | [Effect on evaluation] | [How to avoid next time]
KEY TAKEAWAYS
1. | [Takeaway 1]
2. | [Takeaway 2]
3. | [Takeaway 3]
4. | [Takeaway 4]
5. | [Takeaway 5]
RECOMMENDED TIMELINE FOR FUTURE EVALUATIONS
Phase | Duration | Notes
Initial Compliance Check | 1 week | Can be done in parallel with prep
Detailed Evaluation | 2-3 weeks | Requires dedicated team time
Shortlisting | 1 week | Scoring and analysis
Demos & Clarifications | 2-3 weeks | Scheduling can be challenging
Reference Checks | 1 week | Can overlap with demos
Site Visits (optional) | 1-2 weeks | Only for mission-critical systems
Final Scoring | 1 week | Allow time for team alignment
Recommendation & Approval | 2-3 weeks | Executive calendars
Contract Negotiation | 4-8 weeks | Most variable component
TOTAL DURATION

## 9-Build vs Buy vs Rent
BUILD vs BUY vs RENT DECISION FRAMEWORK
Strategic Decision: How should we acquire the integration platform?
DECISION CRITERIA | BUILD (Mirth Connect) | BUY (InterSystems) | RENT (Cloud SaaS) | Weight | Recommendation
INITIAL INVESTMENT
Upfront Cost | $200K (infra + staff) | $800K (license + impl) | $50K (setup) |  | RENT wins
Time to Deploy | 6-9 months | 4-6 months | 1-2 months |  | RENT wins
Resource Requirements | 5-7 FTEs (dev team) | 2-3 FTEs (config) | 1 FTE (admin) |  | RENT wins
Infrastructure | Self-managed | Self-managed | Vendor-managed |  | RENT wins
ONGOING COSTS (Annual) |  |  |  | 25%
Licensing | $0 (open source) | $150K | $120K (subscription) |  | BUILD wins
Maintenance & Support | $50K (community/3rd party) | $120K (20% of license) | Included in subscription |  | RENT wins
Staffing (operations) | $400K (2 FTEs) | $200K (1 FTE) | $100K (0.5 FTE) |  | RENT wins
Infrastructure/Hosting | $60K | $60K | Included |  | RENT wins
Training | $30K/year | $20K/year | $10K/year |  | RENT wins
5-Year TCO | $2.74M | $2.5M | $1.8M |  | RENT wins
CAPABILITY & FLEXIBILITY
Customization | Unlimited (source code) | Moderate (config) | Limited (API only) |  | BUILD wins
Time to Add Features | Fast (if you have skills) | Moderate | Slow (vendor roadmap) |  | BUILD wins
Integration Patterns | Any (you code it) | Enterprise patterns | Standard patterns only |  | BUILD wins
Vendor Lock-in | None | High | Very High |  | BUILD wins
Technology Control | Full control | Partial control | No control |  | BUILD wins
RISK & SUPPORT
Support Quality | Community-based | 24/7 enterprise | 24/7 enterprise |  | BUY/RENT wins
Security Certifications | None (DIY) | HIPAA, SOC 2, HITRUST | HIPAA, SOC 2 |  | BUY wins
Compliance Burden | 100% on you | Shared responsibility | Vendor-managed |  | RENT wins
Disaster Recovery | You build it | You build it | Vendor-provided |  | RENT wins
Skill Availability | Low (niche skills) | Medium | High (managed) |  | RENT wins
Upgrade Risk | High (manual testing) | Medium | Low (vendor-managed) |  | RENT wins
SCALABILITY & PERFORMANCE
Scale Up/Down | Manual (add servers) | Manual (add licenses) | Automatic (elastic) |  | RENT wins
Performance Optimization | DIY tuning required | Vendor guidance | Vendor-managed |  | RENT wins
Geographic Distribution | You architect it | You architect it | Multi-region ready |  | RENT wins
Peak Load Handling | Pre-provision capacity | Pre-provision capacity | Auto-scale |  | RENT wins
WEIGHTED SCORE CALCULATION
Based on your priorities: | BUILD: 68/100 | BUY: 82/100 | RENT: 85/100
DECISION MATRIX BY SCENARIO
| BUILD | BUY | RENT |  | Best For
Large enterprise (5000+ beds) | ✓ If skilled team | ✓✓ Recommended | ○ Evaluate |  | BUY
Medium hospital (500-5000 beds) | ○ If budget-limited | ✓ Good option | ✓✓ Recommended |  | RENT or BUY
Small hospital (<500 beds) | ✗ Not recommended | ○ May be overkill | ✓✓ Recommended |  | RENT
Health system (multi-facility) | ○ If centralized IT | ✓✓ Recommended | ✓ Consider |  | BUY
Startup/Digital Health | ✓ If tech-focused | ✗ Too expensive | ✓✓ Recommended |  | RENT or BUILD
Highly regulated environment | ✗ Risk too high | ✓✓ Recommended | ✓ If certified |  | BUY
Limited IT staff | ✗ Not feasible | ○ Need support | ✓✓ Recommended |  | RENT
Unique requirements | ✓✓ Recommended | ✓ If customizable | ✗ Too limited |  | BUILD
RECOMMENDATION FOR THIS RFQ
Based on evaluation: | Mirth Connect (BUILD) | InterSystems (BUY) | Consider Cloud Option
Best if you have: | • Strong dev team • Budget constraints • Unique needs | • Enterprise budget • Moderate IT staff • Need support | • Limited IT staff • Fast deployment • Predictable costs
Risks: | • No formal support • Requires expertise • Compliance burden | • High upfront cost • Vendor lock-in • Complex contracts | • Vendor dependency • Limited customization • Data sovereignty

## 10-Complexity Analysis
IMPLEMENTATION COMPLEXITY ASSESSMENT
| Mirth Connect (BUILD) | InterSystems (BUY) | Rhapsody (BUY)
Complexity Factor | Score (1-5) | Risk | Score (1-5) | Risk | Score (1-5) | Risk
TECHNICAL COMPLEXITY
Installation & Configuration | 4 | High | 3 | Medium | 2 | Low
Learning Curve | 4 | High | 3 | Medium | 3 | Medium
Architecture Decisions | 5 | Very High | 2 | Low | 2 | Low
Custom Code Required | 5 | Very High | 2 | Low | 2 | Low
Testing Effort | 5 | Very High | 3 | Medium | 3 | Medium
Performance Tuning | 4 | High | 2 | Low | 2 | Low
Subtotal Technical | 27 |  | 15 |  | 14
INTEGRATION COMPLEXITY
Number of Systems to Integrate | 3 | Medium | 3 | Medium | 3 | Medium
Data Format Diversity | 4 | High | 3 | Medium | 3 | Medium
Message Volume | 3 | Medium | 2 | Low | 2 | Low
Real-time Requirements | 3 | Medium | 2 | Low | 2 | Low
Error Handling Sophistication | 4 | High | 2 | Low | 2 | Low
Subtotal Integration | 17 |  | 12 |  | 12
ORGANIZATIONAL COMPLEXITY
Team Skill Gap | 5 | Very High | 3 | Medium | 3 | Medium
Change Management | 4 | High | 3 | Medium | 3 | Medium
Stakeholder Alignment | 3 | Medium | 3 | Medium | 3 | Medium
Vendor Coordination | 2 | Low | 4 | High | 4 | High
Training Requirements | 5 | Very High | 3 | Medium | 3 | Medium
Subtotal Organizational | 19 |  | 16 |  | 16
OPERATIONAL COMPLEXITY
Ongoing Maintenance | 5 | Very High | 2 | Low | 2 | Low
Support Model | 4 | High | 1 | Very Low | 1 | Very Low
Upgrade Process | 5 | Very High | 3 | Medium | 2 | Low
Monitoring & Alerting | 4 | High | 2 | Low | 2 | Low
Disaster Recovery | 5 | Very High | 3 | Medium | 2 | Low
Subtotal Operational | 23 |  | 11 |  | 9
COMPLIANCE COMPLEXITY
Security Implementation | 5 | Very High | 2 | Low | 2 | Low
Audit Trail Management | 4 | High | 2 | Low | 2 | Low
Regulatory Reporting | 4 | High | 2 | Low | 2 | Low
Data Privacy Controls | 4 | High | 2 | Low | 2 | Low
Certification Process | 5 | Very High | 1 | Very Low | 1 | Very Low
Subtotal Compliance | 22 |  | 9 |  | 9
TOTAL COMPLEXITY SCORE | 108/125 | Very High | 63/125 | Medium | 60/125 | Medium
Complexity Rating | 86% | HIGH RISK | 50% | MODERATE | 48% | MODERATE
COMPLEXITY INTERPRETATION
Score Range | Rating | Risk Level | Recommendation
90-125 (>72%) | Very High | Critical | Requires expert team & strong governance
70-89 (56-72%) | High | Significant | Need experienced team & external support
50-69 (40-56%) | Medium | Moderate | Adequate internal capability with training
30-49 (24-40%) | Low | Manageable | Standard implementation approach
<30 (<24%) | Very Low | Minimal | Straightforward deployment
COMPLEXITY MITIGATION STRATEGIES
| Mirth Connect | InterSystems | Rhapsody
Risk Mitigation | • Hire HL7 experts • Extensive training • Phased rollout • Strong DevOps | • Leverage vendor services • Structured training • Partner with SI | • Use vendor best practices • Engage professional services • Follow reference architectures
Success Factors | • Dev team with Java skills • Clear architecture vision • Time for learning curve • Budget for consultants | • Executive sponsorship • Adequate budget • Vendor partnership • Clear requirements | • Strong project management • Vendor engagement • User training focus • Realistic timeline

## 11-SWOT Analysis
SWOT ANALYSIS - VENDOR COMPARISON
MIRTH CONNECT (Open Source / BUILD Option)
STRENGTHS | WEAKNESSES | OPPORTUNITIES | THREATS
✓ Zero licensing cost | ✗ No formal vendor support | ○ Active open-source community | ⚠ Community support may decline
✓ Full source code access | ✗ Requires strong dev skills | ○ Customizable to any need | ⚠ Staff turnover = knowledge loss
✓ No vendor lock-in | ✗ No certifications (HIPAA, SOC 2) | ○ Learn transferable skills | ⚠ Compliance burden on you
✓ Excellent HL7 v2 support | ✗ FHIR support still maturing | ○ Contribute to FHIR roadmap | ⚠ May lag commercial products
✓ Flexible deployment options | ✗ Manual security hardening | ○ Cloud-native deployment | ⚠ DIY disaster recovery
✓ Large community | ✗ Fragmented documentation | ○ Training resources growing | ⚠ No guaranteed updates/patches
✓ Fast feature development | ✗ Testing burden on you | ○ Control upgrade timeline | ⚠ Compatibility issues with upgrades
✓ JavaScript-based transforms | ✗ Limited GUI tools | ○ IDE integration improving | ⚠ Skilled developers hard to find
BEST FOR: | Not suitable for: | Key Success Factor: | Deal Breaker:
• Budget-constrained orgs • Strong dev teams • Unique requirements • Tech-forward culture | • Risk-averse organizations • Limited IT staff • High compliance needs • Prefer vendor support | Development team with HL7/Java/JavaScript expertise and time to invest | Lack of HIPAA certification and formal SLA guarantees
INTERSYSTEMS HEALTHSHARE (Commercial / BUY Option)
STRENGTHS | WEAKNESSES | OPPORTUNITIES | THREATS
✓ 40+ years in healthcare | ✗ High upfront cost | ○ Cloud offering emerging | ⚠ Complex pricing model
✓ Enterprise-grade platform | ✗ Steep learning curve | ○ FHIR innovation leader | ⚠ Vendor lock-in risk
✓ Excellent FHIR R4 support | ✗ Rigid licensing terms | ○ Growing partner ecosystem | ⚠ Staff costs for Cache developers
✓ Built-in data persistence | ✗ Requires Cache/ObjectScript | ○ AI/ML capabilities roadmap | ⚠ Premium pricing vs competitors
✓ 24/7 enterprise support | ✗ Implementation complexity | ○ Strong healthcare focus | ⚠ Perception as "legacy" platform
✓ All certifications (SOC 2, HITRUST) | ✗ Long procurement cycles | ○ Government/VA contracts | ⚠ Newer cloud-native competitors
✓ Proven at scale | ✗ Heavy infrastructure needs | ○ International expansion | ⚠ Economic downturn = fewer deals
✓ Visual development tools | ✗ Customization can be costly | ○ Unified care record vision | ⚠ Open source alternatives
BEST FOR: | Not suitable for: | Key Success Factor: | Deal Breaker:
• Large health systems • High message volumes • Complex integrations • Need vendor support | • Small/medium hospitals • Limited budgets • Simple integrations • Prefer cloud-first | Executive sponsorship, adequate budget, and long-term commitment | High TCO ($2.5M over 5 years) and vendor lock-in concerns
RHAPSODY INTEGRATION ENGINE (Commercial / BUY Option)
STRENGTHS | WEAKNESSES | OPPORTUNITIES | THREATS
✓ User-friendly interface | ✗ Smaller market share than ISC | ○ Cloud/SaaS offering | ⚠ Acquisition by Orion Health
✓ Excellent documentation | ✗ Fewer pre-built connectors | ○ Asia-Pacific expansion | ⚠ Less innovation than competitors
✓ Strong HL7 v2 capabilities | ✗ FHIR catching up to leaders | ○ Value-based care push | ⚠ Staff familiarity lower
✓ Good price/performance ratio | ✗ Less name recognition | ○ Partnership opportunities | ⚠ Smaller user community
✓ Faster implementation | ✗ Limited enterprise features | ○ Niche in mid-market | ⚠ ISC/Epic competitive pressure
✓ Responsive support | ✗ Not ideal for huge scale | ○ Interoperability mandates | ⚠ Cloud providers (AWS, Azure)
✓ Lower TCO than ISC | ✗ Fewer reference sites | ○ Telehealth integration | ⚠ Economic uncertainty
✓ Good training programs | ✗ Less mature data platform | ○ Focus on usability | ⚠ Mirth/open source pricing
BEST FOR: | Not suitable for: | Key Success Factor: | Deal Breaker:
• Medium-sized hospitals • Ease of use priority • Faster deployment • Mid-range budget | • Very large enterprises • Cutting-edge FHIR needs • Deep data analytics • Brand-conscious buyers | Focus on user experience, vendor partnership, and realistic expectations | Perception as "mid-tier" and smaller ecosystem
COMPARATIVE SWOT SUMMARY
Criterion | Mirth Connect | InterSystems | Rhapsody
Overall Risk Level | HIGH | MEDIUM | MEDIUM
Implementation Risk | Very High | Medium | Low
Operational Risk | High | Low | Low
Financial Risk | Low | High | Medium
Strategic Fit | Tech-forward orgs | Enterprise healthcare | Mid-market hospitals
Recommended If... | Strong dev team + tight budget | Large scale + enterprise needs | Balance of cost + features